## Main
See | https://techformist.com/free-agile-scrum-excel-template
Scrum Project
Product | Parking Garage |  | Date
Git |  |  | Sprint #
Team
Scrum Master |  |  | Team #
Developers
Epic | [5 empty] | Sprint Plan |  | CS275 Garage
Id | Description | Start | End | Status | Remarks | Sprint | Start | End | Status | Story Points (Committed) | Story Points (Delivered) | Scrum Master
1 | Platforms / GUI / Data | 20/Sept/21 | 2021-10-01 |  | VSC and Java, GUI created, Maya SQl | Spr. 1.1 | 2021-09-20 | 2021-10-01 |  |  |  | Vineel
2 | Daily Customer Functionality |  |  |  |  | Spr. 1.2 | 2021-10-04 | 2021-10-15 |  |  |  | Dylan
3 | Long Term Client Functionality |  |  |  |  | Spr. 1.3 | 2021-10-18 | 2021-10-29 |  |  |  | Jonas
[6 empty] | Spr. 1.4 | 2021-11-01 | 2021-11-12 |  |  |  | Nikolai
[6 empty] | Spr. 1.5 | 2021-11-15 | 2021-11-26 |  |  |  | Tristen
[6 empty] | Spr. 1.6 | 2021-11-29 | 2021-12-10 |  |  |  | Tristen
Formulas:
CS275 Garage = [Start]+11
Start = [CS275 Garage, row above]+3

## Backlog
Backlog
Id | Theme | As a.. | I want to .. | so that .. | Acceptance Criteria | Remarks | Priority | Status | Type | Project Id | Sprint Id | Story Points (Est.) | Effort (Actual) | Owner | Status | Remarks
1 |  | Developer | Know what language to use | I can work on the project | The language is decided | Java |  | Complete
4 |  | Developer | Determine what development tools to use | I can work on the project | Tools are installed and usable | VSC and Github |  | Complete
2 |  | Developer | Determine how client is charged | Compute Payments | Client is asked for correct amount | Dylan |  | Complete |  |  |  | 2
3 |  | Developer | Determine what shows on the screen | I can keep track of what the program is doing | When payments are assessed, amount and the name of the client shows on screen | Tristen | [5 empty] | 12
5 |  | Developer | Know what data we are going to store about the customer | I can write the software that stores and access the data | List of information we're storing about client is complete | Jonas |  | Complete |  |  |  | 2021-01-02
6 |  | Developer | Know what the format of the data is for the database | I can write code that puts data in the database and reads data from the database | Data has been written to and retrieved from database | Nikolai |  | complete |  |  |  | 5
7 |  | Developer | Use a system for configuration management | Work on a common development codebase without clobbering others work or introducing errors | CM system has been determined, developer has tried pulling commiting and pushing. | Vineel |  | Complete |  |  |  | 3
8 |  | Developer | Take user input from the GUI to later be stored in database | We can properly charge them | Info can be taken in from the GUI and stored for later | Tristen | [5 empty] | 5
9 |  | Developer | Write methods which can access data from the database. | Others can manipulate the database. | Methods can print out or change database data. | Nikolai | [5 empty] | 4
10 |  | Developer | Track how long a client is using my garage | I know the proper amount to charge them | Be able to store check in time, compare to check out time | Dylan | [5 empty] | 2
11 |  | Developer | Have membership pricing | be able to have members | PriceBracket takes ito account all types of memberships PREREQUISITE: User Story 12 | Dylan/Jonas | [5 empty] | 3
12 |  | Developer | Have a list of all different types of members | be able to create membership pricing | all different types of memberships are listed | Jonas |  | complete |  |  |  | 1
13 |  | developer | ensure the database cannot be altered by irrelevant methods | member data stays constant | database class is fully private | nikolai | [5 empty] | 9
14 |  | developer | Establish a connection to the database | Code can alter database values | the database can be altered and printed out from within java | nikolai | [5 empty] | 10
15 |  | developer | See a list of different members | we can test our code | list of fake members is created | jonas | [5 empty] | 2
16 |  | User | Store my information | the computer remembers me and my membership statue | Store information about users in database | Vineel
17 |  | User | reserve a parking spot | parking is quicker | User can select and reserve spot in the program | VIneel
18 |  | stakeholder | be able to choose the size of the garage | the program is more marketable | The garage can be any size (any number of spots per level) | Tristen | [5 empty] | 5

## Tracker
Sprint Tracker
<- effort / day ->
Sprint Id | Backlog Id | Description | Owner | Status | Story Points (Est.) | Completed | Pending | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10
1.1 | 221 |  |  |  |  | 2 | -2 | 1 |  | 1
1.1 | 224 |  |  |  |  | 1 | -1 |  | 1
1.1 | 225 |  |  |  |  | 5 | -5 |  | 1 |  | 2 |  | 1 | 1
1.1 | 229 |  |  |  |  | 3 | -3 |  |  | 1 |  | 1 |  |  | 1
1.1 | 251 |  |  |  |  | 13 | -13 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
1.1 | 253 |  |  |  |  | 1 | -1 | [9 empty] | 1
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
|  |  |  | Total | 0 | 25 | -25 | 4 | 4 | 3 | 3 | 2 | 2 | 2 | 2 | 1 | 2
|  |  |  | Burn down |  |  |  | -4 | -8 | -11 | -14 | -16 | -18 | -20 | -22 | -23 | -25
|  |  |  | Burn up |  |  |  | 4 | 8 | 11 | 14 | 16 | 18 | 20 | 22 | 23 | 25

## Impediment
Impediments
Id | Description | Raised By | Raised On | Sprint # | Impacted Backlog # | Owner | Status | Resolution | Resolved On | Remarks

## Retrospective
Retrospective Log
Sprint # | Date | Owner | Continue Doing | Start Doing | Stop Doing | Remarks

## Summary
Reports & Dashboards
Sprint Velocity
Burn down Chart | Burn up Chart

## Scrum Master Schedule
Sprint | Scrum Master
1 | Vineel
2 | Dylan
3 | Jonas
4 | Nikolai
5 | Tristen
6 | Tristen

## References
References
External |  | Internal
Description | Link | Description | Link
Glossary & Terminology | https://www.scrumalliance.org/community/articles/2007/march/glossary-of-scrum-terms

## Tristen Tasks
user story #3

## Nikolai Tasks
looking into databases :)

## Jonas Tasks
Looking into releveant data we will need, and anything else that can be turned into variables. | Basic data we need to know about cilents.

## Vineel Tasks
invite schilling to github