## Main
Jonas
| See | https://techformist.com/free-agile-scrum-excel-template
Scrum Project
| Product | Parking Garage |  | Date | 2021-11-15
| Git | https://github.com/vineella/SE-class-parking-garage |  | Sprint # | 4
Team
| Scrum Master | Jonas Ling |  | Team # | 5
| Developers | Tristen
Dylan
Vineella
Nikolai
| Epic | [5 empty] | Sprint Plan |  | CS275 Garage
| Id | Description | Start | End | Status | Remarks | Sprint | Start | End | Status | Story Points (Committed) | Story Points (Delivered) | Scrum Master
| 1 | Platforms / GUI / Data | 20/Sept/21 | 2021-10-01 |  | VSC and Java, GUI created, Maya SQl | Spr. 1.1 | 2021-09-20 | 2021-10-01 |  |  |  | Vineel
| 2 | Daily Customer Functionality |  |  |  |  | Spr. 1.2 | 2021-10-04 | 2021-10-15 |  |  |  | Dylan
| 3 | Long Term Client Functionality |  |  |  |  | Spr. 1.3 | 2021-10-18 | 2021-10-29 |  |  |  | Nikolao
[7 empty] | Spr. 1.4 | 2021-11-15 | 2021-11-26 |  |  |  | Jonas
[7 empty] | Spr. 1.5 | 2021-11-29 | 2021-12-10 |  |  |  | Tristen
[7 empty] | Spr. 1.6 | 2021-11-29 | 2021-12-10
Formulas:
CS275 Garage = [Start]+11
Start = [CS275 Garage, row above]+3

## Backlog
Backlog
Id | Theme | As a.. | I want to .. | so that .. | Acceptance Criteria | Remarks | Priority | Status | Type | Project Id | Sprint Id | Story Points (Est.) | Effort (Actual) | Owner | Status | Remarks
1 |  | Developer | Know what language to use | I can work on the project | The language is decided | Java |  | Complete
4 |  | Developer | Determine what development tools to use | I can work on the project | Tools are installed and usable | VSC and Github |  | Complete
2 |  | Developer | Determine how client is charged | Compute Payments | Client is asked for correct amount | Dylan |  | Complete |  |  |  | 2
3 |  | Developer | Determine what shows on the screen | I can keep track of what the program is doing | When payments are assessed, amount and the name of the client shows on screen | Tristen | Low |  |  |  |  | 12
5 |  | Developer | Know what data we are going to store about the customer | I can write the software that stores and access the data | List of information we're storing about client is complete | Jonas |  | Complete |  |  |  | 2021-01-02
6 |  | Developer | Know what the format of the data is for the database | I can write code that puts data in the database and reads data from the database | Data has been written to and retrieved from database | Nikolai |  | complete |  |  |  | 5
7 |  | Developer | Use a system for configuration management | Work on a common development codebase without clobbering others work or introducing errors | CM system has been determined, developer has tried pulling commiting and pushing. | Vineel |  | Complete |  |  |  | 3
8 |  | Developer | Take user input from the GUI to later be stored in database | We can properly charge them | Info can be taken in from the GUI and stored for later | Tristen | high | complete |  |  |  | 7
9 |  | Developer | Write methods which can access data from the database. | Others can manipulate the database. | Methods can print out or change database data. | Nikolai |  | complete |  |  |  | 4
10 |  | Developer | Track how long a client is using my garage | I know the proper amount to charge them | Be able to store check in time, compare to check out time | Dylan | high | complete |  |  |  | 2
11 |  | Developer | Have membership pricing | be able to have members | PriceBracket takes ito account all types of memberships PREREQUISITE: User Story 12 | Dylan/Jonas |  | complete |  |  |  | 3
12 |  | Developer | Have a list of all different types of members | be able to create membership pricing | all different types of memberships are listed | Jonas |  | complete |  |  |  | 1
13 |  | developer | locate specific data from the database | member data stays constant | the database can be sorted through | nikolai | [5 empty] | 9
14 |  | developer | Establish a connection to the database | Code can alter database values | the database can be altered and printed out from within java | nikolai |  | complete |  |  |  | 10
15 |  | developer | See a list of different members | we can test our code | list of fake members is created | jonas | low | complete |  |  |  | 2
16 |  | User | Store my information | the computer remembers me and my membership statue | Store information about users in database | Vineel | mid | Complete
17 |  | User | reserve a parking spot | parking is quicker | User can select and reserve spot in the program | Vineel | mid | Complete
18 |  | stakeholder | be able to choose the size of the garage | the program is more marketable | The garage can be any size (any number of spots per level) | Tristen | high | complete |  |  |  | 7
19 |  | Developer | Link my gui to the database | Things entered to the GUI save to the database | Person can enter their name and save their information in the database | Dylan/Nikolai/Tristen | extremely high
20 |  | User | Pay extra | My car and items are insured | Pay extra money to buy insurance | Dylan | Low
21 |  | User | Get handicap parking | I do not have to walk too far on my handicap | Allow handicap parking |  | Low
22 |  | Developer | see what cars haven't paid their membership | I can deny them access to the garage | code checks if user is up to date on bills | Vineel | mid | complete
23 |  | User | Go to a vending machine | I can eat | Add in a popup menu that offers snacks | Dylan | Low
24 |  | Developer | consistently have my garage cleaned | Have a somewhat clean garage | Garage sends a message and pays a cleaning company every so often to clean | Jonas | Low
25 |  | Developer | Create a client class | We can store all of the necessary information under the proper variable names | we have a class created with proper variables instantiated | Jonas | high | Complete
26 |  | Developer | Create a garage class | keep track of flow | we have a class created with proper variables instantiated | Vineel | high | Complete
27 |  | Developer | Figure out what needs to be in garage class | Create organizating | list is created | Vineel | high | Complete
28 |  | developer | ensure that a user cannot select impossible options | the code doesn't break | users cannot select to leave a car at a spot that is alredy taken and cannot select to check out of a spot that is not full | tristen | high | complete |  |  |  | 3
29 |  | dev | have all the gui code in one class | it is easier to edit | the current gui classes are all collapsed into one class | tristen | low |  |  |  |  | 3
30 |  | dev | see when a given user checked in and see what spot they are in | verify that they are checking out from the right spot and be able to charge them | the client class has variables for time in and spot # | jonas | high | complete
31 |  | dev | communicate between garage class and GUI | I can create an instance of a garage | GUI can call the garage class | tristen/vineel | high | complete |  |  |  | 5
32 |  | dev | communicate between client class and GUI | I can create an instance of a client | GUI can call the client class | tristen/jonas | high | complete |  |  |  | 5
33 |  | dev | alter code already in the database | client information can be updated | method can change text file data | nikolai
34 |  | dev | add price methods to client class | prices can be communicated to the gui | client class can take time in and time out and create an appropriate price | Vineel+Tristen | high | complete |  |  |  | 10
35 |  | user | display amount charged on the GUI | customers know how much they've been charged | GUI displays amount charged/prices | Tristen | high | complete |  |  |  | 2021-01-02
36 |  | dev | add inputs for user to indicate time in and time out | we can charge correct amounts | GUI has inputs for time in and time out | Tristen | high | complete |  |  |  | 3
37 |  | dev | create ticket method | ticket for the user with all relevant info | ticket being generated and printed | Jonas | high | midway
38 |  | dev | add error management to existing GUI code for the user inputs | users cannot crash program by inputting incorrect things | Code is unbreakable by user inputs to a reasonable degree | Tristen | high | complete |  |  |  | 10
39 |  | dev | make sure the price variable always is a double with exactly 2 decimal places | the customer isn't charged a fake amount of money | price variable is always represented to two decimal places | Vineel | high | complete |  |  |  | 3
40 |  | Dev | Incoperate the more intensive pricing code currently in the "pricebracket" class into the client class | Because the priceBracket class won't be used in the final build; the price calculations will happen within the client class | Pricing code within the client class includes different types of pricing | Dylan | High |  |  |  |  | 5
41 |  | user | see how many spots are available on a given floor before actually clicking into it | I can more easily decide which floor to park on | GUI displays num open spots per floor on floor selection screen | tristen | high (required for minimum viable product) |  |  |  |  | 5
42 |  | dev | have the number of spots open per floor be calculated by a garage class method | user story #41, which is required for the minimum viable product, is able to be completed | this number is accurate and communicable to the GUI (aka exists in the client class) | Vineel | very high |  |  |  |  | 3
43 |  | owner | When program ends, save the state of the garage out to its database including: How many/which spots are taken, How many/which spots are open, and Pertinent information regarding who is in what spot | my garage isn't unusable after the power goes out | When program ends it saves the state of the garage out to its database including: How many/which spots are taken, How many/which spots are open, and Pertinent information regarding who is in what spot | Nikolai+Tristen+Vineel | high |  |  |  |  | 15
44 |  | owner | When the program starts up it reads in state of system from its database before startup | the garage is savable and reusable | When the program starts up it reads in state of system from its database before startup | Nikolai+Tristen+Vineel | high |  |  |  |  | 7

## Tracker
Sprint Tracker
<- effort / day ->
Sprint Id | Backlog Id | Description | Owner | Status | Story Points (Est.) | Completed | Pending | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10
1.1 | 221 |  |  |  |  | 2 | -2 | 1 |  | 1
1.1 | 224 |  |  |  |  | 1 | -1 |  | 1
1.1 | 225 |  |  |  |  | 5 | -5 |  | 1 |  | 2 |  | 1 | 1
1.1 | 229 |  |  |  |  | 3 | -3 |  |  | 1 |  | 1 |  |  | 1
1.1 | 251 |  |  |  |  | 13 | -13 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
1.1 | 253 |  |  |  |  | 1 | -1 | [9 empty] | 1
1.4 | 24 | garage clean | Jonas |  |  | 0 | 0
1.4 | 40 | intensive price coding | dylan |  |  | 0 | 0
1.4 | 41 | spots left on floor | Tristen |  |  | 0 | 0
1.4 | 42 | calculation of open spots | vineel |  |  | 0 | 0
1.4 | 43 | save state of garage to database | nikolai |  |  | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
|  |  |  | Total | 0 | 25 | -25 | 4 | 4 | 3 | 3 | 2 | 2 | 2 | 2 | 1 | 2
|  |  |  | Burn down |  |  |  | -4 | -8 | -11 | -14 | -16 | -18 | -20 | -22 | -23 | -25
|  |  |  | Burn up |  |  |  | 4 | 8 | 11 | 14 | 16 | 18 | 20 | 22 | 23 | 25

## Impediment
Impediments
Id | Description | Raised By | Raised On | Sprint # | Impacted Backlog # | Owner | Status | Resolution | Resolved On | Remarks
1 | database taking longer than expected | Nikolai

## Retrospective
Retrospective Log
Sprint # | Date | Owner | Continue Doing | Start Doing | Stop Doing | Remarks

## Summary
Reports & Dashboards
Sprint Velocity
Burn down Chart | Burn up Chart

## Scrum Master Schedule
Sprint | Scrum Master
1 | Vineel
2 | Dylan
3 | Nikolai
4 | Jonas
5 | Tristen

## References
References
External |  | Internal
Description | Link | Description | Link
Glossary & Terminology | https://www.scrumalliance.org/community/articles/2007/march/glossary-of-scrum-terms

## Tristen Tasks
user story #3

## Nikolai Tasks
looking into databases :)

## Jonas Tasks
Looking into releveant data we will need, and anything else that can be turned into variables. | Basic data we need to know about cilents.

## Vineel Tasks
invite schilling to github